## Sheet2
MCI Project Weekly Time Sheet
Team | 21 | Student ID | a1692335 |  |  | Week starting: | 2017-05-15
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2017-05-15 | 8:00 | 0:00 | 4 | Change the function to delete a Select C file from local conmputer | Delete C file | delete.php
Tuesday | 2017-05-16 | 14:00 | 6:00 | 4 | Client Meeting, reallocate the next stage's workload | More clear of the next stage's tasks | Minutes
Wednesday | 2017-05-17 | 13:00 | 18:00 | 5 | Redesign the databse for students' information | Rebuild the database for students' information | studentlist.sql clientlist.sql
Thursday | 2017-05-18 | 8:00 | 12:00 | 4 | Redesign the databse for students' information | Rebuild the database for students' information | studentlist.sql clientlist.sql
Friday | 2017-05-19 | 20:00 | 22:00 | 2 | Test and change the system to assist while loop | System can deal with while loop | result.gdb
Saturday | 2017-05-20 | 11:00 | 16:00 | 5 | Change the gdb file to only keep two decimal places | Make the correct solution more acceptly | result.gdb
Sunday | 2017-05-21 | 9:00 | 13:00 | 4 | Change the display of the solutions | Delete the solution for the firstly of C file | upload_solution.php
|  |  | Total | 28