## Sheet2
MCI Project Weekly Time Sheet
Team | 21 | Student ID | a1674472 |  |  | Week starting: | 2017-03-27
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2017-03-27 | 19:00 | 23:00 | 4 | Learn PHP from youtube tutorial, finish the function of submit button and collect questions | Finish submit button and collect questions | student_tracetable.php, Some notes and questions
Tuesday | 2017-03-28 | 14:00 | 17:00 | 3 | Meeting with supervisor, reallocate the next stage's workload | Tasks for next week are listed and our questions about requirements are answered | Minutes
Wednesday | 2017-03-29 | 19:00 | 21:00 | 2 | Learn PHP from youtube tutorial and design the format of login page | Finish design of login page | login.php and some notes
Thursday | 2017-03-30 | 14:00 | 18:00 | 4 | Learn PHP from youtube tutorial and finish the content on the login page | Finish creation of login page | login.php
Friday | 2017-03-31 | 19:00 | 23:00 | 4 | Learn how to connect login page to database | connection with database for login | login.php and some notes
Saturday | 2017-04-01 | 10:00 | 0:00 | 2 | Finish the connection between login page and database | Finish connection with database for login | login.php, some notes and sql
Sunday | 2017-04-02 | 13:00 | 18:00 | 5 | Make connection between login page and two modes | Finish connection with two modes for login | login.php, some notes and sql
|  |  | Total | 24